## Sheet1
2024 ACA Rate Filing Timeline for Insurers
DATE | ACTIVITY
February 21st, 2023 | Release Draft Guidance
February 28th, 2023 | Insurer comments on draft guidance & survey responses due | Key
March 16th-17th, 2023 | Release Final PY23 Guidance |  | PID releases document
May 17th, 2023 | Rate, Form, and Binder filings due |  | Insurer due date
June 9th, 2023 | (or earlier) Send first round of questions to insurers |  | PID communication to insurer
June 21st, 2023 | (or earlier) First round insurer responses due |  | CMS-related activity
June 30th, 2023 | Risk Adjustment results released
July 7th, 2023 | (or earlier) Send second round of questions to insurer, if needed, as well as notify insurers of any redaction changes needed or new redactions permitted
July 14th, 2023 | (or earlier) Refilings to reflect updated RA results and any redaction updates & second round insurer responses due
July 19th, 2023 | (or earlier) Send third round of questions to insurers, if needed, as well as notify insurers of any redaction changes needed or new redactions permitted
July 21st, 2023 | (or earlier) Third round insurer responses due
July 27th-August 1st, 2023 | Post initial May submission rate filings on Department website
August 16th, 2023 | Final rate filings and QHP templates based on final rate due in SERFF
October 16th, 2023 | Final rates due in HIOS-- Submission deadline for final rate filing justifications that include a QHP into the URR module of HIOS in states with a State-based Exchange that does not use the HealthCare.gov platform Deadline
Note: Dates are subject to change. Insurers may receive more or less than two rounds of questions, depending on the thoroughness of their initial filing and of their responses to PID questions.