## Sheet1
ACA RATE REVIEW TIME LINE - Plan Year 2019
PERIOD | ACTIVITY
2018-02-14 | Release draft guidance
2018-02-23 | Issuer comments on draft guidance due
2018-03-13 | Release final guidance
2018-03-15 | Small group Q3-4 filings due | Key
2018-05-21 | Deadline for rate, form, and binder filings |  | PID releases document
2018-06-15 | Send first round of questions to issuers (or earlier) |  | Issuer due date
2018-06-22 | First round issuer responses due (or earlier) |  | PID communication to issuer
2018-06-29 | Risk adjustment results released
2018-07-06 | Send second round of questions to issuers, if needed, as well as notify issuers of any redaction changes needed or new redactions permitted (or earlier)
2018-07-13 | Refilings to reflect updated RA results and any redaction updates & responses to second round of questions due
2018-07-17 | Send third round of questions to issuers, if needed, as well as notify issuers of any redaction changes needed or new redactions permitted (or earlier)
2018-07-19 | Third round issuer responses due (or earlier)
2018-07-23 | Post complete post-RA rate filings on Department website
2018-08-15 | Deadline for final rate filings and QHP templates based on final rate determinations
2018-08-22 | Final rates due in HIOS
Note: Dates are subject to change. Issuers may receive more or less than two rounds of questions, depending on the thoroughness of their initial filing and of their responses to Departmental questions.